## topic_ranking
Rank	Points			Topic
	Pascal	Gabriel	Sum
2	6	9	15	Natural Language generation
6	10	5	15	Machine Translation
1	4	10	14	Sarcasm Detection
4	7	7	14	Domain Adversarial Training for Sentiment Analysis
7	8	4	12	Character-based CNN for POS Tagging
3	3	8	11	Paraphrase Detection using bi-CNN
9	9	2	11	Dialog Act Classification from Speech&Text
5	2	6	8	Paraphrase Generation
10	5	1	6	Language-independent Emotion Recognition from Speech
8	1	3	4	Multitask Learning: POS & NER

## project_plan
Deadlines		Milestone	Time / (in days total)
data until 23 Dec	data after holidays		data until 23 Dec	data after holidays
Dec 28, 17	Jan 11, 18	Basic setup of data, software & project	6	4
Jan 14, 18	Jan 23, 18	Training cycle of base model(1)	17	12
Jan 18, 18	Jan 26, 18	Test of base model, visualizations	4	3
Feb 4, 18	Feb 5, 18	Individual research, test & visualization	17	10
Feb 7, 18	Feb 7, 18	Poster setup & printing	3	2
Feb 8, 18	Feb 8, 18	Poster presentation	1	1
Mar 1, 18	Mar 1, 18	Documentation	21	21
Mar 8, 18	Mar 8, 18	Summary deadline	1	1
(1)Iterations trough preprocessing, model-choice, hyperparameter optimization			70	54